## Template
|  |  | 02.10.2023-08.10.2023 | 09.10.2023-15.10.2023 | 16.10.2023-22.10.2023 | 23.10.2023-29.10.2023 | 30.10.2023-05.11.2023 | 06.11.2023-12.11.2023 | 13.11.2023-19.11.2023 | 20.11.2023-26.11.2023 | 27.11.2023-03.12.2023 | 04.12.2023-10.12.2023 | 11.12.2023-17.12.2023 | 18.12.2023-24.12.2023 | 25.12.2023-31.12.2023 | 01.01.2024-07.01.2024 | 08.01.2024-14.01.2024 | 15.01.2024-21.01.2024
Start Date: 16/10/2023 |  |  | WEEK 1 | WEEK 2 | WEEK3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Forms |  | week(1-2-3)
Creating a Project Proposal Form | Team | bar: WEEK 1 to WEEK 2
Creating a Project Selection Form | Team | bar: WEEK 1 to WEEK 2
Creating a Project Work Plan | Team | bar: WEEK 1 to WEEK3
Literature Review |  | week(3-6)
Dyslexia diagnosis,dyslexia grouping in the field of health | Kutay | bar: WEEK3 to WEEK 6
Dyslexia treatment in the field of health | Mert | bar: WEEK3 to WEEK 6
Software tools used for dyslexia diagnosis | Göktuğ | bar: WEEK3 to WEEK 6
Software tools used for dyslexia treatment | Pınar | bar: WEEK3 to WEEK 6
Similar mobile applications and their software tools | Beyza | bar: WEEK3 to WEEK 6
Project Webpage |  | week(6-11)
Creating a web page | Kutay | bar: WEEK 6 to WEEK 7; WEEK 11
Creating a web page | Mert | bar: WEEK 6 to WEEK 7; WEEK 11
Software Requirements Specification(SRS) |  | week(6-10)
Specific Requirements (External Interface Requirements/Wireframes) | Beyza | bar: WEEK 6 to WEEK 10
General Description Part(Use-case Diagrams) | Pınar | bar: WEEK 6 to WEEK 10
Introduction | Kutay | bar: WEEK 6 to WEEK 10
Other Non-functional Requirements | Kutay | bar: WEEK 6 to WEEK 10
Specific Requirements (Functional Requirements /Data Flow Diagrams) | Mert | bar: WEEK 6 to WEEK 10
Specific Requirements (Functional Requirements /Activity Diagrams) | Göktuğ | bar: WEEK 6 to WEEK 10
Software Design Description(SDD) |  | week(10-13)
Design Viewpoints | Beyza | bar: WEEK 10 to WEEK 13
Design Viewpoints | Pınar | bar: WEEK 10 to WEEK 13
Overview | Kutay | bar: WEEK 10
Definitions | Kutay | bar: WEEK 10
Conceptual model for software design descriptions | Kutay | bar: WEEK 12 to WEEK 13
Design description information content | Mert | bar: WEEK 10; WEEK 12 to WEEK 13
Design description information content | Göktuğ | bar: WEEK 10 to WEEK 13
Project Report / Tracking Form |  | week(14)
Project Report | Team | bar: WEEK 14
Project Tracking Form | Team | bar: WEEK 14

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#NAME? |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder